## Sayfa1
CankayaUniversity/ceng-407-408-2022-2023-Speech-Emotion-Recognition
Begin Date 24/10/2022 |  | 2022-10-14 | 2022-10-17 | 2022-10-20 | 2022-10-21 | 2022-10-28 | 2022-11-11 | 2022-12-09 | 2022-12-16 | 2022-12-30 | 2023-01-06 | 2023-01-23 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 7 24 2023 | 2023-04-14 | 2023-04-21 | 2024-04-28 | 2024-05-05 | 2024-05-12 | 2024-05-19 | 2024-05-26 | 2024-06-02 | 2024-06-09 | 2024-06-10
Action Steps (What Will Be Done) | Status | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15 | Week15
Project Proposal Form | Done | bar: 2022-10-21 to 2022-10-28
Team Setup | Done | bar: 2022-10-14 to 2022-10-20
Project Selection Form | Done | bar: 2022-10-20
GitHub Repository | Done | bar: 2022-10-20
Project Work Plan | Done | bar: 2022-10-28 to 2022-11-11
Literature Review | Done | bar: 2022-10-21 to 2022-11-11
Software Requirements Specification | Done | bar: 2022-11-11 to 2022-12-09
Project Webpage | Done | bar: 2022-11-11 to 2022-12-16
Software Design Description | Done | bar: 2022-12-16 to 2022-12-30
Project Report / Project Tracking Form | Done | bar: 2022-12-30 to 2023-01-06
Presentation | Done | bar: 2023-01-23
Updated Project Work Plan / LR / SRS / SDD | Done | bar: 2023-03-03 to 2023-03-31
Test Plan Document | Done
Interactive-Demo | Done
Final Product 1st Release | Done
User Manual | Done
Project Report / Test Results / Project Tracking Form | Done
Project Poster | Done
Updated Project Webpage | Done
Demo Video | Done
Presentation | Done